# BIM • CAD • Clash Detection • 4D Analysis

Guidelines, Prompts, and Standard Operating Procedures (SOPs) for Implementation

Owner: Ricardo Portillo (Senior Project Planner/Scheduler)

Version: 1.0  |  Date: 2026-03-01

## How to Use This Document

Copy the relevant prompts verbatim into your AI assistant when starting a task.

Use the SOPs by discipline to standardize inputs/outputs and decision-making.

Do not assume missing data. Always capture gaps and generate an RFI/clarification list.

For reports, keep outputs in tables. Keep language factual and reference drawing/model sources.

## Master Expert Identity Prompt (Use at Session Start)

Paste this at the beginning of every AI session to define the expert role and working standards.

You are a multidisciplinary BIM/CAD engineering expert across Architectural, Structural, Civil, and MEP systems. You can read drawings, specs, RFIs, and schedules; interpret IFC/Revit metadata; and perform constructability and sequencing reviews. Your objectives: (1) Parse provided materials and extract factual, structured data; (2) Compile an accurate project representation; (3) Identify gaps and inconsistencies; (4) Produce meeting-ready outputs (tables, lists, and clear actions). Do not assume missing data.

## Parsing & Data Extraction Prompt Library

Use these prompts to extract quantitative and qualitative data from drawings, specs, PDFs, and models.

### Prompt: Parse PDF Drawings and Extract Key Information

Instruction: Paste this and attach PDFs/drawings.

Parse the drawings and extract: (1) Scope summary; (2) Dimensions; (3) Levels/grades/elevations; (4) Materials and construction types; (5) Structural systems; (6) MEP system types and equipment tags; (7) Gridlines/reference points; (8) Key/general notes. Present results in structured tables by discipline and level. Identify missing or conflicting information explicitly.

### Prompt: Parse IFC/Revit Model Metadata

Extract: element categories; families/types; quantities/dimensions; materials; hosted dependencies; level/workset assignments; MEP system connectivity. Summarize inconsistencies and elements missing required parameters. Return clean tables.

### Prompt: Generate Quantity Takeoffs (QTO)

From the provided model/data, produce QTOs for concrete, steel, framing, ductwork, piping, cable trays, and major equipment. Include formulas or measurement bases and list any assumptions. Flag incomplete data.

## Compilation & Project Representation Prompt Library

### Prompt: Build a Structured Project Dataset

Combine extracted data into a project dataset including: (1) Room/Space database; (2) Equipment database; (3) System hierarchies; (4) QTOs; (5) Constraints and dependencies. Return as tables grouped by Level/Zone and Discipline.

### Prompt: Constructability Analysis

Create a constructability review covering: work areas and access constraints; temporary works; work sequencing; safety/clearances; trade dependencies. Provide step-by-step findings and specific recommendations.

### Prompt: Baseline 4D Sequence Overview

Using the dataset, outline a baseline 4D sequence: build order; ties to major components; prerequisites; long-lead items and procurement risks.

## QA & Validation Prompt Library

### Prompt: Cross-Document Inconsistency Check

Compare drawings/specs/RFIs to identify: conflicting dimensions; design discrepancies; missing info; scope gaps; uncoordinated details. List issues with references and recommended RFIs.

### Prompt: Engineering Logic Validation

Validate structural feasibility, MEP coordination, architectural clearances, and code-related concerns. Flag issues with reasoning and corrective actions.

## Clash Detection Prompt Library (3D)

These prompts cover setup, detection, de-duplication, triage, reporting, and change tracking.

### Prompt: Define Clash Tests & Tolerances

Create a clash test matrix with: test name; Set A vs Set B; filters (levels, zones, worksets, authors); tolerances (hard=0 mm; soft clearances by system); rules (ignore insulation/hangers; include sleeves); expected outcomes and priorities. Output table + concise definitions.

### Prompt: Selection Set Rules (Navisworks/IFC Semantics)

Provide human-readable selection logic for Structure (framing, columns, floors), Ducts (exclude insulation), Pipes (CHW/HHW/DHW/SAN/Fire), Cable Trays, and Architectural (walls, ceilings, stairs, shafts). Flag missing parameters and propose fallbacks.

### Prompt: Clearance Standards (Soft Clashes)

Propose system-specific soft clearances: Duct–Duct 25 mm; Duct–Pipe 25 mm; Pipe–Tray 13 mm; equipment service clearances per parameter; access panels min 600x600 mm. Return rules and data sources (parameter/spec/assumption).

### Prompt: Run & De-duplicate Clashes

Given clash results, remove exact duplicates, group near-duplicates by root-cause, assign system owner, and score priority using severity×impact×schedule criticality×rework risk. Return grouped issue list with counts and priorities.

### Prompt: False Positive Filtering

Filter out likely false positives: temporary elements; dev/test worksets; supports/hangers within 10 mm; insulation-only collisions unless service clearance violated. Provide a log of excluded items with justification.

### Prompt: Reporting (RFI-Ready Language)

For each high-risk clash, draft: issue statement with location; element IDs and systems; why it conflicts; proposed options (pros/cons); decision owner; needed-by date tied to schedule. Produce both a table and a one-paragraph narrative.

### Prompt: Change Tracking Between Model Versions

Compare Clash Set Vn vs Vm to categorize: resolved, persistent, new, regressions. Provide trends and burndown to milestone.

## 4D Clash Analysis Prompt Library (Space + Time)

Use these prompts to detect spatiotemporal conflicts and sequencing risks tied to schedule logic.

### Prompt: Element-to-Activity Mapping

Map BIM elements to activities by Level/Zone/Grid, Discipline/System, Worksets/IFC Class, and WBS/Activity IDs. Highlight unlinked elements and missing metadata.

### Prompt: Temporal Overlap Detection

Identify 4D clashes where activities overlap in the same Level/Zone/Grid or access/staging area. Report overlaps, severity, and schedule impact.

### Prompt: Access & Sequencing Violations

Detect conflicts: equipment blocking access; shafts occupied during riser install; ceiling rough-in overlapping with inspections; walls closing before MEP QA/QC; obstructed crane/hoist paths. List activity IDs and mitigations.

### Prompt: Trade Stacking & Congestion

Find zones where >2 trades are scheduled simultaneously. Report trades, approximate crew counts, congestion risk, and resequencing options.

### Prompt: Logistics & Material Flow Conflicts

Detect laydown conflicts, crane swing overlaps, hoist schedule conflicts, prefab/field overlaps, and access gate congestion. Tie mitigations to logic changes.

### Prompt: Severity & Delay Exposure

Score each 4D clash (1–5) using temporal overlap, critical path, congestion, downstream blocking, and rework risk. Estimate potential delay days and propose mitigation windows.

### Prompt: What-If & Recovery Planning

Simulate impacts of delays, resequencing, exclusive access windows, or crew changes. Recommend actions to protect dry-in, ceiling close-in, and commissioning milestones.

## Sample Outputs (Templates)

Use these as examples of expected deliverables. Adapt field names to your tools (Navisworks, Synchro, P6, ACC, Revizto).

### Sample: Clash Issue Log (3D)

| ID | Test | Type | Level | Zone | Grid | System A | System B | Owner | Priority | Status | Due |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CLSH-001 | Duct_vs_Structure_L3 | Hard | L3 | B | C/6-E/10 | Duct | Beam | MEP Lead | High | Open | 2026-03-20 |
| CLSH-002 | Pipe_vs_Wall_L2 | Soft | L2 | South | D/4 | Pipe | Wall | Plumbing Lead | Medium | Open | 2026-03-18 |

### Sample: 4D Clash Register

| 4D ID | Level | Zone | Grid | Activity A | Dates A | Activity B | Dates B | Overlap (days) | Critical Path | Mitigation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4D-045 | L2 | South Wing | D/4 | A-34150 Duct Rough-In | 05/10–05/20 | A-35210 Wall Framing | 05/15–05/18 | 3 | Yes | Delay framing 4 days or accelerate duct install |
| 4D-046 | L3 | Zone C | E/8 | A-41020 Ceiling Close-in | 06/12–06/14 | A-40600 Above Ceiling Inspection | 06/13–06/13 | 1 | At Risk | Shift inspection or pull close-in by 1 day |

### Sample: Coordination RACI

| Task | BIM/VDC | Architecture | Structure | MEP | Planning/Scheduling | Field Eng. | PM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Define clash tests | R | C | C | C | I | I | A |
| Run clash & group | R | I | I | I | I | I | A |
| 4D mapping | C | I | I | I | R | C | A |
| Issue log & RFIs | R | A | A | A | C | C | A |
| Mitigation & resequence | C | C | C | C | R | R | A |

## Standard Operating Procedures (SOP) by Discipline

### SOP — BIM/VDC Coordination

Collect latest federated model and discipline models (version/date).

Establish selection sets and clash tests; document tolerances and rules.

Run clash; de-duplicate; group by root cause; assign owners and priorities.

Publish issue log (CSV/BCF) and viewpoints with consistent naming.

Re-run after updates; issue delta report (new/resolved/persistent).

Outputs: Clash matrix, issue log, delta report, viewpoints.

### SOP — Architecture

Validate wall types, fire ratings, shafts, and service clearances.

Review clashes involving architectural elements and service clearances/access panels.

Coordinate with MEP for ceiling plenum zoning and equipment access.

Approve penetrations and sleeves locations; align with firestopping requirements.

Outputs: Approved penetrations plan, updated walls/ceilings, access panel matrix.

### SOP — Structure

Review penetrations through slabs/walls and impacts to reinforcement.

Resolve duct/pipe vs beam/slab conflicts; confirm sleeve sizes and locations.

Validate embeds and supports readiness vs schedule.

Update model to reflect approved openings and sleeves.

Outputs: Openings schedule, sleeve matrix, updated structural model.

### SOP — MEP (Mechanical, Electrical, Plumbing, Fire)

Confirm system types, sizes, and elevations; tag equipment with service clearances.

Resolve MEP–MEP and MEP–Structure/Arch clashes with reroutes/resizing as needed.

Validate access/maintenance zones; ensure code-required clearances.

Coordinate hangers/supports and insulation impacts.

Outputs: Updated MEP routing, equipment clearance register, hanger/support plan.

### SOP — Planning/Scheduling (4D)

Align WBS/Activity IDs with model elements (by Level/Zone/System).

Run 4D overlap analysis; identify critical path–related conflicts.

Quantify delay exposure and propose resequencing/mitigation options.

Publish weekly 4D clash register and decision deadlines to protect milestones.

Outputs: 4D clash register, mitigation plan, protected milestone tracker.

### SOP — Field Engineering

Validate constructability and access routes on site.

Confirm temporary works and material handling paths.

Provide as-built feedback to close clashes before installation.

Verify pre-cover inspections scheduled before close-in.

Outputs: Site access plan, redlines/as-built notes, inspection checklist.

### SOP — Project Management & Governance

Set weekly coordination cadence and SLAs for responses/resolution.

Maintain decision register and RFI log linked to issues.

Track trends (new/resolved/persistent) and enforce burndown toward milestones.

Escalate critical risks affecting dry-in, close-in, or commissioning.

Outputs: Decision register, RFI list, trend dashboard, risk escalations.

## Appendix A — Meeting Template

Inputs: latest model, clash re-run, delta trends, schedule extract.

Agenda: Top 10 risks, new vs persistent, required decisions, schedule impacts.

Deliverables: Updated issue log (CSV/BCF), viewpoints, decision register, RFI list.

## Appendix B — Naming Conventions

Issue ID: {Level_Zone}-{SystemA_vs_SystemB}-{Grid}-{ShortDesc}

Viewpoint: {LVL_ZONE}_{AREA}_{GRID}_{DESC}_{NN}

Activities: {WBS}-{Discipline}-{Location}-{Seq}